## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) |  |  |  |  | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Kick-off meeting | 1 | 1 | 1 | 1 | 1
Follow-up/team setup meeting | 1 | 1 | 1 | 1 | 1
First project sponsor meeting | 1 | 1 | 1 | 1 | 1
Internal progress review with guidance advisor | 1 | 1 | 1 | 1 | 1
SharePoint project folder setup | 1 | 1 | 1 | 1 | 1
Notion Scrum/Kanban board setup | 1 | 1 | 1 | 1 | 1
GitHub repository setup | 1 | 1 | 1 | 1 | 1
Project Charter | 1 | 2 | 1 | 2 | 1
Article research and literature review | 1 | 3 | 1 | 3 | 0.6
Existing AI tool review | 2 | 3 | 2 | 3 | 0.8
Student sentiment survey planning | 2 | 3 | 2 | 3 | 0.7
Stakeholder analysis | 2 | 2 | 2 | 2 | 1
Functional requirements | 2 | 2 | 2 | 2 | 0.9
Non-functional requirements | 2 | 2 | 2 | 2 | 0.9
Mental model | 2 | 2 | 2 | 2 | 0.8
Conceptual model | 2 | 2 | 2 | 2 | 0.8
Pre-project planning document | 2 | 2 | 2 | 2 | 1
Ethical AI and Data Privacy Policy | 2 | 2 | 2 | 2 | 0.8
Low-fidelity wireframe | 2 | 2 | 2 | 2 | 1
Sequence diagrams | 2 | 2 | 2 | 2 | 1
Use case diagram | 3 | 2 | 3 | 2 | 0.4
Activity diagram | 3 | 2 | 3 | 2 | 0.3
Figma UI/UX research | 2 | 4 | 2 | 4 | 0.8
Figma prototype | 4 | 4 | 4 | 4 | 0.2
Database and data planning | 4 | 3 | 4 | 3 | 0.3
Software architecture planning | 4 | 3 | 4 | 3 | 0.3
AI/Llama planning | 4 | 4 | 4 | 4 | 0.3
Project Plan drafting | 4 | 6 | 4 | 6 | 0.2
Project Plan review and submission | 10 | 2 | 10 | 2 | 0
Part B development setup | 13 | 2 | 13 | 2 | 0
Front-end development | 14 | 4 | 14 | 4 | 0
Back-end development | 14 | 5 | 14 | 5 | 0
Database setup and integration | 15 | 4 | 15 | 4 | 0
AI integration and AI summon feature | 15 | 5 | 15 | 5 | 0
PDF handling and file processing | 16 | 4 | 16 | 4 | 0
System integration | 17 | 4 | 17 | 4 | 0